## OEPP During DB Process
#VALUE! | NCDOT Open-Ended Performance Plan
Include PDF of all sheets included in the proposal submitted during DB Procurement

## OEPP Proposed
#VALUE! |  | NCDOT Open-Ended Performance Plan
Contract:
Prime Contractor:
Date of Execution | 2024-08-01
Total Construction Value: | 100000000
DBE Contractual Goal (%): | 7%
DBE Contractual Goal ($) | 7000000
Anticipated Participation by Contract Year
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6
DBE Types of Subcontracting | DBE Scope of Work | Commitment ($) | Anticipated Commitment Date (Quarter/Year) | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total Participation
Concrete Flatwork | Curb and Gutter, Sidewalk, WCR | 1500000 | Q3 2026 | Anticipated Participation by Contract Year Year 3 2026: 250000; Anticipated Participation by Contract Year Year 4 2027: 1000000; Anticipated Participation by Contract Year Year 5 2028: 250000 | 1500000
Hauling | Hauling Earthwork (Pd by Hour) | 1000000 | Q2 2025 | Anticipated Participation by Contract Year Year 2 2025: 250000; Anticipated Participation by Contract Year Year 3 2026: 350000; Anticipated Participation by Contract Year Year 4 2027: 400000 | 1000000
Erosion Control | Seeding and Mulching, Basin Construction, EC Devices | 2000000 | Q2 2025 |  | 700000 | 500000 | 500000 | 300000 |  | 2000000
Erosion Control | Permit Delineation | 500000 | Q1 2025 | Anticipated Participation by Contract Year Year 2 2025: 500000 | 500000
Guardrail | Guardrail | 1000000 | Q3 2026 | Anticipated Participation by Contract Year Year 3 2026: 250000; Anticipated Participation by Contract Year Year 4 2027: 500000; Anticipated Participation by Contract Year Year 5 2028: 250000 | 1000000
Pavement Marking | Thermo, Paint, Poly, | 1000000 | Q1 2027 | Anticipated Participation by Contract Year Year 4 2027: 300000; Anticipated Participation by Contract Year Year 5 2028: 700000 | 1000000
0
0
| Total Anticipated Commitment: | 7000000 | Total | 0 | 1450000 | 1350000 | 2700000 | 1500000 | 0 | 7000000
|  |  | % | 0% | 20.71% | 19.29% | 38.57% | 21.43% | 0% | 100%
|  |  | % Total | 0% | 20.71% | 40% | 78.57% | 100% | 100%

## OEPP Commitments
#VALUE! |  | NCDOT Open-Ended Performance Plan
Contract:
Prime Contractor: |  |  | DBE Commitments Met: | 7168000
Date of Execution | 2024-08-01 |  | DBE % Committed | 102.4%
Total Construction Value: | 100000000
DBE Contractual Goal (%): | 7% |  | DBE Payments to Date: | 7291000
DBE Contractual Goal ($) | 7000000 |  | DBE % Based on Payments | 104.2%
Anticipated Participation by Contract Year
[7 empty] | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 4 |  |  | Year 5 |  |  | Year 6
[7 empty] | 2024 |  |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028 |  |  | 2029 |  |  | Total Contract
DBE Scope of Work | DBE Firm Name Committed | Subcontract # | Approval Date | OEPP Proposed Amount | Actual Commitment | Difference | Target Participation | DBE Payments Made to Sub | Difference | Target Participation | DBE Payments Made to Sub | Difference | Target Participation | DBE Payments Made to Sub | Difference | Target Participation | DBE Payments Made to Sub | Difference | Target Participation | DBE Payments Made to Sub | Difference | Target Participation | DBE Payments Made to Sub | Difference | Total Participation | Does Total Participation by Year meet commitment amount | Total Payments | Committed Amount Left | % Commitment Achieved | Commmitment Met
Curb and Gutter, Sidewalk, WCR | We Know Concrete | 5 | 2026-04-01 | 1500000 | 1542000 | 42000 | 0 |  | 0 | 0 |  | 0 | 250000 | 260000 | 10000 | 980000 | 950000 | -30000 | 312000 | 200000 | -112000 |  | 130000 | 130000 | 1542000 | YES | 1540000 | 2000 | 99.87% | NO
Hauling Earthwork (Pd by Hour) | Hauling Inc. | 2A - 2nd tier sub to Grading Inc | 2025-03-30 | 1000000 | 1050000 | 50000 | 0 |  | 0 | 230000 | 200000 | -30000 | 350000 | 400000 | 50000 | 400000 | 380000 | -20000 |  | 100000 | 100000 |  |  | 0 | 980000 | NO | 1080000 | -30000 | 110.2% | YES
Seeding and Mulching, Basin Construction, EC Devices | Erosion Control R Us | 7 | 2025-01-23 | 2000000 | 2050000 | 50000 | 0 |  | 0 | 700000 | 650000 | -50000 | 500000 | 680000 | 180000 | 500000 | 500000 | 0 | 300000 | 450000 | 150000 |  |  | 0 | 2000000 | NO | 2280000 | -230000 | 114% | YES
Permit Delineation | Fencing All Day | 1 | 2025-04-01 | 500000 | 500000 | 0 | 0 |  | 0 | 500000 | 501000 | 1000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 500000 | YES | 501000 | -1000 | 100.2% | YES
Guardrail | Rail In Time | 10 | 2026-04-15 | 1000000 | 1056000 | 56000 | 0 |  | 0 | 0 |  | 0 | 250000 | 240000 | -10000 | 500000 | 400000 | -100000 | 250000 | 250000 | 0 |  |  | 0 | 1000000 | NO | 890000 | 166000 | 89% | NO
Thermo, Paint, Poly, | Striping the World | 12 | 2026-11-30 | 1000000 | 970000 | -30000 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 300000 | 300000 | 0 | 700000 | 680000 | -20000 |  | 20000 | 20000 | 1000000 | YES | 1000000 | -30000 | 100% | YES
0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | YES | 0 | 0 | #DIV/0! | YES
0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | YES | 0 | 0 | #DIV/0! | YES
|  |  | Total | 7000000 | 7168000 | 168000 | 0 | 0 | 0 | 1430000 | 1351000 | -79000 | 1350000 | 1580000 | 230000 | 2680000 | 2530000 | -150000 | 1562000 | 1680000 | 118000 | 0 | 150000 |  | 7022000 |  | 7291000 | -123000
|  |  | % | 100% | 102.4% | 2.4% | 0% | 0% |  | 20.43% | 19.3% |  | 19.29% | 22.57% |  | 38.29% |  |  | 22.31% |  |  | 0% |  |  | 100.3% |  | 104.2%
|  |  | Cumulative $ Totals |  |  |  | 0 | 0 |  | 1430000 | 1351000 |  | 2780000 | 2931000 |  | 5460000 | 5461000 |  | 7022000 | 7141000 |  | 7022000 | 7291000
|  |  | Cumulative % Totals |  |  |  | 0% | 0% |  | 20.43% | 19.3% |  | 39.71% | 41.87% |  | 78% | 78.01% |  | 100.3% | 102% |  | 100.3% | 104.2%

## Modification History
#VALUE! | NCDOT Open-Ended Performance Plan
Contractor Request | Approved/Denied | Version of OEPP | Date Action Took | Approval/Rejection Comments | CCU Comments | OCR Comments
OEPP Submitted | Approved | 1 | 2024-07-30 | Initial OEPP Approved | Review and recommend approval | Reviewed and recommend approval
Commitment for Erosion Control R Us | Approved | 2 | 2025-01-23 | Sent OCR Letter of Intent - Meets Requirements for OEPP
Commitment for Fencing All Day | Approved | 3 | 2025-04-01 | Sent OCR Letter of Intent - Permit Areas Required Less Delinetion than originally anticipated | Review and recommend approval | Reviewed and recommend approval